## Features
Project: Canary Music Streaming Service
Team: 5
| ID | Feature Name | Description | Remark
| UC01 | Listen to songs | The users can play the songs via the music player.
| UC02 | Find | Users want to browse through lists of songs, artists, and playlists.
| UC03 | Create playlists | The users can gather songs and create their own playlists.
| UC04 | Upload songs | Users can upload their songs to share them with the community
| UC05 | Resolve requests | Admins need to resolve the requests sent by other users.

## Test cases
Feature ID | Case ID | Test case name | Actors | Note / Pre-condition | Test step | Expected Result (ER) | Actual Result | Status | Tester | Tested Date | Remark
UC01 | UI01 | Test playing a song | Guests, Members, Admins | A song is being played | 1. Hit the Play button | The song should be continued playing if is currently paused | The same ER | Pass | Đoàn Đặng Phương Nam | 2024-02-12
UC01 | UI02 | Test pausing a song | Guests, Members, Admins | A song is being played | 1. Hit the Pause button | The song should be paused if is currently played | The same ER | Pass | Đoàn Đặng Phương Nam | 2024-02-12
UC01 | UI03 | Test replaying a song | Guests, Members, Admins | A song is being played | 1. Hit the Replay button | The song should be replayed from the beginning | The same ER | Pass | Đoàn Đặng Phương Nam | 2024-02-12
UC01 | UI04 | Test forwarding a song | Guests, Members, Admins | A song is being played | 1. Choose somewhere randomly in the progress bar | The song should be skipped to the chosen part of the progress bar and continue playing | The same ER | Pass | Đoàn Đặng Phương Nam | 2024-02-12
UC01 | UI05 | Test playing the previous song in a playlist | Guests, Members, Admins | A playlist is being played | 1. Hit the previous button | If it is the first song in the playlist, skip to the last song. Else, play the previous song | When hitting the previous button from the current song is the first song of the playlist, the music player still plays the first song. Other cases are similar with the ER | Fail | Đoàn Đặng Phương Nam | 2024-02-12
UC01 | UI06 | Test playing the next song in a playlist | Guests, Members, Admins | A playlist is being played | 1. Hit the next button | If it is the last song in the playlist, skip to the first song. Else, play the next song | When hitting the next button from the current song is the last song of the playlist, the music player still plays the last song. Other cases are similar with the ER | Fail | Đoàn Đặng Phương Nam | 2024-03-12
UC01 | UI07 | Test playing playlist songs in shuffle mode | Guests, Members, Admins | A playlist is being played | 1. Hit the shuffle button | The play order in the playlist will be shuffle randomly | The order of the song stated the same | Fail | Đoàn Đặng Phương Nam | 2024-03-12
UC02 | UI01 | Test seeking a song that exists in the database | Guests, Members, Admins | "Heavy is the crown" exists in database | 1. Enter keyword: "Heavy is the crown" 2. Hit Enter | The correct song should be displayed in the song tab | The same ER | Pass | Bùi Nguyễn Lan Vy | 2024-02-12
UC02 | UI02 | Test seeking a playlist that exists in the database | Guests, Members, Admins | "Imagin Dragon" exists in database | 1. Enter keyword: "Imagin Dragon" 2. Hit Enter | The correct playlist should be display in the playlist tab | The same ER | Pass | Bùi Nguyễn Lan Vy | 2024-02-12
UC02 | UI03 | Test seeking an artist that exists in the database | Guests, Members, Admins | "huhehu" exists in database | 1. Enter keyword: "huhehu" 2. Hit Enter | The correct artist should be display in the artist tab | No result is displayed | Fail | Bùi Nguyễn Lan Vy | 2024-04-12
UC02 | UI04 | Test seeking an item with the blank field | Guests, Members, Admins |  | 1. Input nothing 2. Hit Enter | Should notice that nothing is inputed | Nothing happens | Fail | Bùi Nguyễn Lan Vy | 2024-02-12
UC02 | UI05 | Test seeking a song that does not exist in the database | Guests, Members, Admins | No song named "Song1234" in the DB | 1. Enter a keyword: "Song1234" 2. Hit Enter | Should notice that nothing is found | The same ER | Pass | Bùi Nguyễn Lan Vy | 2024-04-12
UC02 | UI06 | Test seeking a playlist that does not exist in the database | Guests, Members, Admins | No playlist named "Playlist1234" in the DB | 1. Enter a keyword: "Playlist1234" 2. Hit Enter | Should notice that nothing is found | The same ER | Pass | Trần Anh Minh | 2024-04-12
UC02 | UI07 | Test seeking an artist that does not exist in the database | Guests, Members, Admins | No artist named "Artist1234" in the DB | 1. Enter a keyword: "Artist1234" 2. Hit Enter | Should notice that nothing is found | The same ER | Pass | Trần Anh Minh | 2024-04-12
UC02 | UI08 | Test seeking a song with a partial name | Guests, Members, Admins | "Heavy is the crown" exists in database | 1. Enter the a part of the song: "Heavy" 2. Hit Enter | The song should be displayed in the search result | The same ER | Pass | Trần Anh Minh | 2024-04-12
UC02 | UI09 | Test seeking a playlist with a partial name | Guests, Members, Admins | "Imagin Dragon" exists in database | 1. Enter the a part of the playlist: "Imagi" 2. Hit Enter | The playlist should be displayed in the search result | The same ER | Pass | Trần Anh Minh | 2024-05-12
UC02 | UI10 | Test seeking an artist with a partial name | Guests, Members, Admins | "huhehu" exists in database | 1. Enter the a part of the artist's name: "huh" 2. Hit Enter | The artist should be displayed in the search result | The same ER | Pass | Trần Anh Minh | 2024-05-12
UC03 | UI01 | Test adding a song to a playlist | Guests | User has not logged-in | 1. Play a song 2. Hit the Add to playlist button | The system will require the user to be logged in | The system redirects to the Log in page | Pass | Đoàn Đặng Phương Nam | 2024-03-12
UC03 | UI02 | Test adding a song to existed playlist | Members, Admins | User must logged in to the system Exists playlist "ABC" | 1. Play a song 2. Hit the icon of Add to playlist 3. Choose the playlist "ABC" | The current song will be added into the chosen playlist | The same ER | Pass | Đoàn Đặng Phương Nam | 2024-03-12
UC03 | UI03 | Test adding a song to new playlist | Members, Admins | User must logged in to the system No playlist named "TPL" | 1. Play a song 2. Hit the icon of Add to playlist 3. Choose to create new playlist and name it "TPL" | A new playlist is created. The current song will be added to that playlist. | The same ER | Pass | Trần Anh Minh | 2024-05-12
UC03 | UI04 | Test removing a song from a playlist | Members, Admins | User must logged in to the system The song "Heavy is the crown" is in playlist "ABC" | 1. Enter the playlist page from Library 2. Choose the "ABC" playlist 3. Locate the song "Heavy is the crown" 4. Hit Remove | The song will be removed from the playlist | The song has not been removed | Fail | Bùi Nguyễn Lan Vy | 2024-04-12
UC03 | UI05 | Test re-adding a song to a playlist | Members, Admins | User must logged in to the system The song "Heavy is the crown" is already in the "ABC" playlist | 1. Play a song "Heavy is the crown" 2. Hit the Add to playlist button 3. Choose the "ABC" playlist | The system will notice the song has already inside the playlist | No duplicated songs recorded | Pass | Trần Anh Minh | 2024-05-12
UC04 | UI01 | Test uploading a valid song | Members, Admins | User must logged in to the system | 1. Hit the Upload button 2. Provide the song information 3. Upload the song file 4. Hit OK | A request will be sent to the admins to be verified The song will be uploaded to the temporary database | There are no requests sent to the admins to be verified The song has not been uploaded to the temporary database | Fail | Trần Anh Minh | 2024-09-12
UC04 | UI02 | Test uploading with data overlimit song | Members, Admins | User must logged in to the system The limit usage: 50 MB | 1. Hit the Upload button 2. Provide the song information 3. Choose song file that overlimit capactity | The song will not be uploaded The system will notice the song passed the storage limit | The same ER | Pass | Đoàn Đặng Phương Nam | 2024-09-12
UC04 | UI03 | Test uploading with missing information | Members, Admins | User must logged in to the system | 1. Hit the Upload button 2. Provide missing song's information 3. Hit OK | The system will notice that there are blanks | The same ER | Pass | Bùi Nguyễn Lan Vy | 2024-09-12
UC04 | UI04 | Test uploading existed song | Members, Admins | User must logged in to the system | 1. Hit the Upload button 2. Enter the pre-occupied song name 3. Hit OK | The system will denied the upload, will notice the song is existed | The same ER | Pass | Bùi Nguyễn Lan Vy | 2024-09-12
UC04 | UI05 | Test uploading unsupported file type | Members, Admins | Supported file types: MP3, WAV, FLAC, M4A, WMA, AAC, AIF and AIFF. | 1. Hit the Upload button 2. Choose an unsupport file type | The system will notice the song was not uploaded as unsupport file type | The same ER | Pass | Bùi Nguyễn Lan Vy | 2024-09-12
UC05 | UI01 | Test resolving acceptable song upload | Admins | Require Admin account | 1. Enter the Admin option 2. Choosing the Upload tab 3. Choose a upload request to review 4. Hit Approve | The song will be recognized as a normal song and be transfered from temporary database to main database A notification is sent to the user announce that the song was approved | The song has been upload successfully | Pass | Trần Anh Minh | 2024-10-12
UC05 | UI02 | Test resolving unacceptable song upload | Admins | Require Admin account | 1. Enter the Admin option 2. Choosing the Upload tab 3. Choose a upload request to review 4. Hit Deny | The song will be removed from the temporary database A notification will be sent to the user announce that the song was denied | The song has not been removed from the temporary database No notification is sent | Fail | Đoàn Đặng Phương Nam | 2024-10-12
UC05 | UI03 | Test resolving acceptable report | Admins | Require Admin account | 1. Enter the Admin option 2. Choosing the Report tab 3. Choose a report to review 4. Hit Approve | The report song will be removed down from the database A notification will be sent to the song's owner and the reported user | The song has not been removed and there is no notification | Fail | Trần Anh Minh | 2024-10-12
UC05 | UI04 | Test resolving unacceptable report | Admins | Require Admin account | 1. Enter the Admin option 2. Choosing the Report tab 3. Choose a report to review 4. Hit Deny | Nothing will happen A notification will be sent to the reported user | No notification recorded | Fail | Trần Anh Minh | 2024-10-12